## Sheet1
Activity Number | Activity Name | Activity Name Description | Number of days | Start Date | Dependency | Milestone
Iteration 1 |  |  | 55 | June 8, 2016
1 | Requirements | Research Documentations | 15 | June 8, 2016 |  | Good Quality Documentation
2 | Analysis | System Examination | 5 | June 8, 2016
3 | Design | System Architecture | 7 | July 4, 2016 |  | Detailed Design
4 | Code | System Development | 15 | July 12, 2016 |  | Initial Prototype
5 | Test | Software Testing | 3 | August 3, 2016
5.1 | Alpha Testing | In-house Testing | 3 | August 10, 2016
6 | User Acceptance | Application Testing | 3 | August 24, 2016
6.1 | Beta Testing | Field Trials | 3 | September 5, 2016
7 | Learnings | Acquired Knowledge | 1
Iteration 2 |  |  | 47
1 | Requirements | Research Documentations | 5 | September 21, 2016
2 | Analysis | System Examination | 3 | September 27, 2016 |  | Detailed Research Study
3 | Design | System Architecture | 7 | October 4, 2016
4 | Code | System Development | 7 | October 19, 2016
5 | Test | Software Testing | 1 | November 7, 2016
5.1 | Alpha Testing | In-house Testing | 1 | November 9, 2016
6 | User Acceptance | Application Testing | 3 | November 23, 2016
6.1 | Beta Testing | Field Trials | 3 | December 12, 2016
7 | Learnings | Acquired Knowledge | 1
8 | Deployment | Software Implementation | 16 | 2016-12-15
9 | Maintenance | System Maintenance |  | 2016-01-01
Iteration 3 |  |  | 47
1 | Requirements | Research Documentations | 3 | January 11, 2017
2 | Analysis | System Examination | 3 | January 16, 2017
3 | Design | System Architecture | 5 | January 23, 2017
4 | Code | System Development | 5 | February 4, 2017
5 | Test | Software Testing | 1 | February 15, 2017
5.1 | Alpha Testing | In-house Testing | 1 | March 1, 2017
6 | User Acceptance | Application Testing | 3 | March 15, 2017
6.1 | Beta Testing | Field Trials | 3 | April 3, 2017
7 | Learnings | Acquired Knowledge | 1
8 | Deployment | Software Implementation | 25 | May 15, 2016
9 | Maintenance | System Maintenance |  | June 6, 2016
Note on E2: Jameiah Nicole: SYADD1
Note on E3: Jameiah Nicole: SYADD1
Note on E6: Jameiah Nicole: July 28 end of Coding
Note on E10: Jameiah Nicole: First Prototype presentation to sir Sean //SYADD1
Note on E13: Jameiah Nicole: CSPROJ
Note on E20: Jameiah Nicole: Week before Finals in CSPROJ
Note on I23: Jameiah Nicole: SOFTDEV
Note on E25: Jameiah Nicole: SOFTDEV