## Sheet1
Activity Number | Activity Number | Activity Name | Number of Days | Start Date | Dependency | Milestone
1 | Management | Project Documentation | 5 | February 2, 2016 |  | Good Quality Documentation
1.1 | Gather Information |  | 3 | February 9, 2016
1.1.1 | Interview Adviser |  | 1 | February 15, 2016
1.1.2 | Interview Client |  | 1 | February 15, 2016
1.2 | Create Document |  | 15 | January 26, 2016
1.2.1 | Create Project Context |  | 1 | February 16, 2016
1.2.2 | Create Purpose & Description |  | 1 | February 1, 2016
1.2.3 | Create Objectives |  | 1 | February 2, 2016
1.2.4 | Scope and Limitations |  | 1 | February 8, 2016
1.2.5 | Create Related Studies |  | 5 | February 9, 2016
1.2.6 | Create Related Systems |  | 5 | February 9, 2016
1.3 | Present Document |  | 1 | April 5, 2016
1.3.1 | Present to Adviser |  | 1 | March 31, 2016
1.3.2 | Present to Client |  | 1 | March 31, 2016
2 | Design | System Design | 15 | September 19, 2016 |  | Detailed Design
2.1 | Prepare first Design |  | 20 | September 25, 2016
2.1.2 | Create all required diagrams |  | 5 | October 10, 2016
2.1.3 | Create Database Desiagn |  | 5 | October 10, 2016
2.2 | Prepare Detailed Design |  | 3
2.2.1 | Develop Site Design |  | 5
2.3 | Document Design | Software Prototype | 1 | October 24, 2016
2.3.1 | Document Design Specification |  | 1
2.4 | Present Document
2.4.1 | Present to Adviser |  | 1
2.4.2 | Present to Client |  | 1
3 | Build | System Development | 30 |  |  | Software Code
3.1 | Develop Software | System Programming | 15
3.1.2 | Develop user interface |  | 5
3.1.3 | Develop Front End |  | 3
3.1.4 | Develop Back End |  | 3
3.1.5 | Develop Server |  | 2
3.2 | Hardware |  | 3
3.2.1 | Server |  | 3
3.3 | Software Packages |  | 1
3.3.1 | PHP |  | 1
3.3.2 | Database MySql | System Debugging | 1
3.3.3 | Operating System - Windows |  | 1
3.4 | Perform Integration Testing |  | 2
3.5 | Present System
3.5.1 | Present to Client |  | 1
3.5.2 | Present to Adviser |  | 2
5 | Implementation | System Execution | 30
4.1 | Implement Redesign Web Site |  | 5
4.2 | Provide 24/7 Web Site Support |  | 5
4.2.1 | Support until the end of term |  | 12
4.3 | Present Status |  | 1
4.3.1 | Present to Adviser |  | 1
4.3.2 | Present to Client |  | 1
4.4 | QA/QC Checklist |  | 1
5 | Training | Software Presentation | 3
5.1 | Provide Training |  | 3
5.1.1 | Train Adviser |  | 5
5.1.2 | Train Client |  | 5
5.2 | Present Status |  | 1
5.2.1 | Present to Adviser |  | 1
5.2.2 | Present to Client |  | 1
5.3 | QA/QC Checklist |  | 1
7 | Handoff | System Transaction | 15
7.1 | Provide all documentation |  | 3
7.2 | Present Closure Report |  | 3
7.2.1 | Present to Adviser for Review |  | 3
7.2.2 | Present to Client for Approval |  | 3
7.3 | QA/QC will complete Checklist |  | 2